## Qualitative Risks
Risk |  |  | Pre-mitigation |  |  |  |  | Response |  |  | Post-mitigation |  |  |  |  | Details
ID | Type | Title | Probability | Schedule | Cost | Performance | Score | Strategy | Title | Total Cost | Probability | Schedule | Cost | Performance | Score | Owner | Description | Cause | Effect | Category | Trigger | Status | Proximity | Start Date | End Date | Exposure/EMV | Quantifiable Risk | Notes
R001 | Threat | Approval bottlenecks | H | VH | H | M | 35 | Mitigate | Streamlining Approval Process | 520000 | M | M | L | M | 25 | Regulatory Affairs Manager | Project delays and cost overruns due to regulatory hurdles | Regulatory delays in obtaining necessary approvals. | Project timelines extended, leading to cost overruns and potential penalties under contracts. | Process | Regulatory approval delays | Open | Mid Term | 2008-04-01 | 2008-09-30 | 180000 | true | Implementing a proactive strategy for managing regulatory approvals to minimize delays.
R002 | Threat | Equity Risk | L | M | M | L | 49 | Transfer | Diversification of Investment Portfolio | 440000 | L | L | M | H | 15 | Investment Manager | Financial strain and potential ownership dilution from inadequate equity support. | Insufficient equity contribution from NBVL. | Financial strain, higher debt burden, and potential dilution of ownership stake. | Financial | Over-commitment of equity | Open | Imminent | 2008-06-01 | 2008-11-30 | 64000 | true | Implementing a diversified investment strategy to mitigate concentration risk in equity allocation.
R003 | Threat | Labor Strikes | H | H | H | H | 35 | Contingency | Develop Contingency Plans | 300000 | VL | L | L | M | 3 | Human Resources Manager | Work stoppages due to labor disputes | Unforeseen union actions | Delays in project milestones | Labor | Union disagreements | Open | Mid Term | 2008-09-01 | 2009-02-28 | 90000 | true | Maintain good relations with unions, have contingency plans.
R004 | Threat | Health Risk | L | H | M | M | 17 | Enhance | Enhance Safety Protocols | 250000 | L | M | L | L | 3 | Chief Medical Officer | Workplace accidents and injuries | Lack of safety protocols | Potential fines and reputational damage | Health and Safety | Inadequate safety procedures | Open | Immediate | 2008-11-01 | 2009-01-31 | 50000 | true | Implement strong health protocols, conduct regular screenings
R005 | Opportunity | Political Risk | M | M | L | L | 18.3 | Engage | Stakeholder Engagement | 200000 | VL | H | L | VL | 3 | Government Relations Manager | Changes in government policies | Political elections | Changes in project execution, delays | Political | Modifications to government policy | Open | Long Term | 2009-01-01 | 2009-04-30 | 50000 | true | Assess political risks, build local relationships.
R006 | Threat | Regulatory Risk | H | H | VH | H | 56 | Compliance | Mitigate by ensuiring thorough legal review & compliance checks | $ 31,00,000.00 | L | L | L | L | 27 | Compliance Officer, Legal Counsel | Risk of non-compliance with laws and regulations | Changing regulations and lack of awareness | Fines, legal issues, and product changes | Compliance Risk | Changes in relevant laws or regulations | Open | Mid Term | 2009-07-01 | 2010-03-31 | 250000 | true | Regular legal reviews and updates
R007 | Threat | Experienced Staff Shortage | H | H | H | H | 49 | Mitigation | Mitigate by investing in training & hiring initiatives | $ 33,00,000.00 | M | M | M | M | 25 | Project Manager | Risk of not having enough skilled staff | High Demand for experienced staff & limited availablity | Slower development & potential quality issues | Resource Risk | High turnover rates or recruitment challenges | Open | Mid Term | 2009-09-01 | 2009-12-31 | 231000 | true | Continuous recruitment and training programs in place
R008 | Threat | Force Majeure Risk | M | VH | H | H | 23 | Contingency | Insurance, Disaster Management plan | 1000000 | L | M | M | VH | 12.6 | Project Manager | Unavoidable natural disasters or events beyond human control. | Acts of nature, war, civil unrest | Project delays, increased costs, potential loss of life or assets | External | Occurrence of a natural disaster or civil unrest | Open | Distant | 2009-11-01 | 2010-03-31 | 160000 | false | Review insurance policies regularly and update disaster recovery plans.
R009 | Threat | Financial Closure Risks | M | H | L | H | 30 | Mitigate | Ensuring Financial Closure | 450000 | M | M | M | H | 30 | Chief Financial Officer | Funding shortages leading to project delays or cancellation. | Inadequate funding or inability to secure project financing. | Delays in project execution, increased financing costs, and potential contractual breaches. | Financial | Market conditions | Open | Imminent | 2008-05-01 | 2008-12-31 | 180000 | true | Negotiating with banks and financial institutions to secure additional financing options.
R010 | Threat | Fuel Risk | M | H | H | H | 35 | Mitigate | Securing Fuel Supply | 560000 | H | M | M | H | 42 | Procurement Manager | Operational disruptions and higher costs from unreliable coal supply. | Disruptions in coal supply from logistical or geopolitical issues. | Operational interruptions, increased operational costs, and potential penalties under power purchase agreements. | Operational | Reliance on single source | Open | Mid Term | 2008-07-01 | 2009-03-31 | 150000 | true | Exploring alternative suppliers and negotiating stable supply contracts to mitigate risks.
R011 | Threat | Infrastructure Risk | L | M | H | H | 19 | Strengthen | Improve Supply Chain Resilience | 400000 | L | L | M | L | 11 | Facilities Manager | Inadequate supporting infrastructure | Delays in infrastructure development | Inefficiencies in project execution | Infrastructure | Delays in infrastructure | Open | Mid Term | 2009-03-01 | 2009-12-31 | 100000 | true | Enhance resilience through maintenance and contingency plans.
R012 | Opportunity | Technical Risk | M | L | M | H | 25 | Continous Improvement | Leverage cutting edge technology & continous improvement | 500000 | L | L | L | L | 9 | Engineering Lead | Opportunity to enhance capabilities & reliability | Adoption of advanced technologies & best practices | Increased user satisfaction & trust in the product | Operational | Implementation of new technologies or methodologies | Open | Mid Term | 2009-04-01 | 2009-07-31 | 150000 | true | Regular updates & innovations planned
R013 | Threat | Off-take Risk | M | M | M | M | 25 | Mitigation | Mitigate through targeted market & user engagement | 220000 | M | M | VH | VH | 38 | ML | Risk of low user adoption or usage rates | Misalignment with user needs or preferences | Reduced user base and engagement | Market Risk | Low initial user sign-ups or engagement metrics | Open | Mid Term | 2009-05-01 | 2009-10-31 | 110000 | true | User feedback integration into development
R014 | Threat | Budget Overrun | H | M | VH | H | 28 | Contingency | Cost Optimization | 800000 | M | L | H | M | 15 | Chief Financial Officer | Exceeding the planned budget due to unforeseen expenses | Inflation, scope creep, inefficiencies | Financial Strain, potential need for additional funding | Schedule | Unforeseen expenses | Open | Mid Term | 2010-01-01 | 2010-12-31 | 300000 | true | Implement strict change control and cost reviews
R015 | Threat | Time Overrun | M | VH | M | H | 21 | Contingency | Critical Path Analysis, Resource leveling | 500000 | L | M | M | M | 10 | Project Manager | Failure to complete the project within the planned timeline | Resource constraints, technical issues, external dependencies | Delayed benefits, potential penalties, loss of goodwill | Cost | Unforeseen delays | Open | Mid Term | 2010-03-01 | 2011-03-31 | 195000 | true | Identify delays, Re-assign resources
R016 | Opportunity | Interest rate fluctuation | M | L | H | M | 14 | Transfer | Fixed-rate financing, Interest rate swaps | 2000000 | L | L | M | L | 7.3 | Chief Financial Officer | Uncertainty in interest rates leading to increased financing costs | Economic instability, central bank policies, market speculation | Higher debt servicing costs, potential need for additional funding | Cost | Changes in central bank interest rates or market indicators | Open | Mid Term | 2010-05-01 | 2010-10-31 | 1360000 | true | Monitor market trends and consider locking in interest rates through hedging instruments.
R017 | Threat | Exchange Rate Risk | M | H | M | M | 30 | Mitigate | Currency Risk Mitigation Framework | 370000 | L | L | L | VL | 6 | Chief Financial Officer | Potential cost variability due to fluctuations in foreign exchange rates, affecting the budget and financial stability of the project | Dependency on foreign suppliers and services priced in foreign currencies combined with volatile global currency markets | Increased procurement and operational costs, leading to budget overruns and potential adjustments in project financial planning. | Financial | Sudden significant fluctuations in currency exchange rates | Open | Imminent | 2008-05-01 | 2008-12-31 | 206250 | true | Regularly review and adjust currency hedging strategies to respond to market changes and protect project budget integrity
R018 | Threat | Cybersecurity Risk | M | L | H | M | 15 | Mitigate | Cybersecurity Breach | 550000 | M | L | H | M | 22 | IT Security Team | There is a potential for a cybersecurity breach compromising sensitive project data and operational systems due to insufficient security measures and vulnerabilities in the network infrastructure. | Insufficient cybersecurity measures, vulnerabilities in network infrastructure, or phishing attacks targeting project personnel. | Data loss, system downtime, reputational damage, financial losses due to regulatory fines or legal fees. | Operational | Phishing attack, malware infiltration, or unauthorized access attempt. | Open | Mid Term | 2008-06-01 | 2008-10-06 | 207000 | true | Ensure immediate implementation of enhanced cybersecurity protocols, regular security audits, and employee training to mitigate risks effectively.
R019 | Opportunity | Reputational risk | L | H | H | VH | 15 | Mitigate | Enhanced Stakeholder Engagement | 500000 | VL | L | M | M | 4 | Project Manager | Negative public perception leading to loss of investor confidence and potential project opposition | Public concern over environmental impact and community opposition | Reduced investor confidence, potential project delays, and increased costs due to opposition | Strategic | Negative media coverage or public protests | Open | Imminent | 2010-03-01 | 2011-03-31 | 96250 | false | Implementing a comprehensive communications plan to address stakeholder concerns and improve transparency.
R020 | Threat | Competitor Innovations | M | M | H | H | 35 | Strengthen | Differentiation through Environmental and Efficiency Standards | 400000 | M | M | H | H | 35 | CTO or COO | Competitor innovations in technology could lead to operational inefficiencies | Rapid technological advancements | Reduced operational efficiency and competitiveness | Strategic | Technological change | Open | Mid Term | 2011-04-06 | 2011-05-12 | 162000 | true | NBEIL needs to continually invest in R&D and technology upgrades to mitigate this risk.
R021 | Threat | Supply chain risk | M | H | H | M | 31 | Diversification | Multiple sourcing | 500000 | L | M | M | L | 13 | Supply Chain Manager | Risk of delays or quality issues from key suppliers. | Dependence on single or few suppliers. | Project delays, increased costs, reduced performance. | Operational | Delivery delays, quality issues. | Open | Mid Term | 2011-05-11 | 2011-10-20 | 200000 | true | Regularly review supplier performance.

## Quantitative Risks
Scenario Name | ID | Title | Probability | Mitigation Cost | Mitigation Actions
Pre Mitigation | R001 | Approval bottlenecks | 60% | 300000 | Implement a streamlined regulatory approval process with dedicated follow-ups.
Pre Mitigation | R002 | Equity Risk | 20% | 320000 | Diversify equity sources and establish contingency plans with alternative investors.
Pre Mitigation | R003 | Labor Strikes | 30% | 150000 | Maintain positive labor relations and implement contingency plans
Pre Mitigation | R004 | Health Risk | 20% | 100000 | Ensure robust health protocols and conduct regular health screenings.
Pre Mitigation | R005 | Political Risk | 25% | 100000 | Conduct political risk assessments and establish local relationships.
Pre Mitigation | R006 | Regulatory Risk | 60% | 250000 | Mitigate by ensuring thorough legal review & compliance checks
Pre Mitigation | R007 | Experienced Staff Shortage | 70% | 231000 | Mitigate by investing in training & hiring initiatives
Pre Mitigation | R008 | Force Majeure Risk | 20% | 800000 | Review insurance policies regularly and update disaster recovery plans.
Pre Mitigation | R009 | Financial Closure Risks | 50% | 360000 | Engage multiple lenders and prepare thorough financial documentation.
Pre Mitigation | R010 | Fuel Risk | 60% | 250000 | Secure long-term fuel contracts and explore fuel price hedging options.
Pre Mitigation | R011 | Infrastructure Risk | 25% | 200000 | Enhance infrastructure resilience with maintenance and contingency plans.
Pre Mitigation | R012 | Technical Enhancement | 60% | 300000 | Leveraging cutting-edge technology & contious improvement
Pre Mitigation | R013 | Off-take Risk | 50% | 220000 | Mitigate through targeted marketing & user engagement
Pre Mitigation | R014 | Budget Overrun | 60% | 500000 | Implement strict change control and cost reviews
Pre Mitigation | R015 | Time Overrun | 65% | 300000 | Identify delays, Re-assign resources
Pre Mitigation | R016 | Interest rate fluctuation | 85% | 1600000 | Monitor market trends and consider locking in interest rates through hedging instruments.
Pre Mitigation | R017 | Exchange rate risk | 55% | 375000 | Implement currency hedging and maintain multi-currency accounts
Pre Mitigation | R018 | Cybersecurity Risk | 60% | 345000 | Implement immediate and robust cybersecurity measures, conduct frequent security audits to identify and rectify vulnerabilities, and provide comprehensive employee training to recognize and prevent phishing attacks and other cyber threats.
Pre Mitigation | R019 | Reputational risk | 25% | 385000 | Implementing a comprehensive communications plan to address stakeholder concerns and improve transparency.
Pre Mitigation | R020 | Competitor Innovations | 60% | 270000 | To mitigate competitor innovation risks, NBEIL should monitor market trends closely and invest in R&D while forging strategic partnerships to enhance technological capabilities and innovation agility.
Pre Mitigation | R021 | Supply chain risk | 40% | 500000 | Diversification of suppliers, Multiple sourcing

## Response Actions
Mitigation Details |  |  |  | Task/Work Details | [7 empty] | Post-Mitigation Position
Name | Risk ID | Description | Responsibility | Start | Finish | Target Start | Target Finish | Mitigation Cost | Actual Cost | Task/WBS | Status | Probability | Schedule | Cost | Performance | Score
Streamlining Approval Process | R001 | Establish a dedicated regulatory team and use tracking systems for proactive approval management. | Regulatory Affairs Manager | 2008-04-01 | 2008-09-30 | 2008-04-01 | 2008-09-30 | 300000 | 0 | 1.1.1 | InProgress | M | M | L | M | 25
Diversification of Investment Portfolio | R002 | Diversify equity sources and maintain strong investor relations. | Investment Manager | 2008-06-01 | 2008-11-30 | 2008-06-01 | 2008-11-30 | 320000 | 0 | 1.1.2 | Proposed | L | L | M | H | 15
Develop Contingency Plans | R003 | Prepare alternative action plans for potential disruptions | Human Resources Manager | 2008-09-01 | 2009-02-28 | 2008-09-01 | 2009-02-28 | 150000 | 0 | 1.1.3 | Proposed | L | M | M | L | 13
Enhance Safety Protocols | R004 | Strengthen measures to ensure workplace safety. | Chief Medical Officer | 2008-11-01 | 2009-01-31 | 2008-11-01 | 2009-01-31 | 100000 | 0 | 1.1.4 | Proposed | M | L | M | L | 18
Stakeholder Engagement | R005 | Foster communication with all project stakeholders. | Government Relations Manager | 2009-01-01 | 2009-04-30 | 2009-01-01 | 2009-04-30 | 100000 | 0 | 1.2.1 | Proposed | M | M | M | M | 25
Regulatory Compliance | R006 | Risk of non-compliance with laws and regulations | Compliance Officer, Legal Counsel | 2009-07-01 | 2010-03-31 | 2009-07-01 | 2010-03-31 | 310000 | 0 | 1.2.2 | InProgress | H | H | H | VH | 54
Skilled Staff Acquisition | R007 | Risk of not having enough skilled staff | Project Manager | 2009-09-01 | 2009-12-31 | 2009-09-01 | 2009-12-31 | $330,00.00 | 0 | 1.2.3 | InProgress | H | H | H | H | 49
Insurance, Disaster Management plan | R008 | Utilize Business Interruption Insurance and/or Implement disaster management plans | Project Manager | 2009-11-01 | 2010-03-31 | 2009-11-01 | 2010-03-31 | 800000 | 0 | 1.2.4 | Proposed | L | M | M | VH | 13
Ensuring Financial Closure | R009 | Engage multiple lenders and ensure comprehensive financial documentation. | Chief Financial Manager | 2008-05-01 | 2008-12-31 | 2008-05-01 | 2008-12-31 | 360000 | 0 | 1.3.1 | InProgress | M | M | M | H | 30
Securing Fuel Supply | R010 | Secure long-term fuel contracts and explore fuel price hedging options. | Procurement Manager | 2008-07-01 | 2009-03-31 | 2008-07-01 | 2009-03-31 | 250000 | 0 | 1.3.2 | Proposed | H | M | M | H | 42
Improve Supply Chain Resilience | R011 | Strengthen supply chain to withstand disruptions. | Facilities Manager | 2009-03-01 | 2009-12-31 | 2009-03-01 | 2009-12-31 | 200000 | 0 | 1.3.3 | Proposed | L | L | L | M | 11
Technical Enchancement | R012 | Opportunity to enhance capabilities & reliability through leveraging cutting-edge technology and continuous improvement. | Engineering Lead | 2009-04-01 | 2009-07-31 | 2009-04-01 | 2009-07-31 | 500000 | 0 | 1.3.4 | Proposed | M | M | L | H | 25
User Adoption | R013 | Risk of low user adoption or usage rates due to misalignment with user needs or preferences. | Marketing Manager | 2009-01-01 | 2009-10-31 | 2009-05-01 | 2009-10-31 | 220000 | 0 | 1.4.1 | Proposed | M | M | M | M | 25
Cost Optimization | R014 | Implement strict change control and cost reviews | Chief Financial Manager | 2010-01-01 | 2010-12-31 | 2010-01-01 | 2010-12-31 | 500000 | 0 | 1.4.2 | Proposed | M | L | H | M | 15
Critical Path Analysis, Resource leveling | R015 | Identify delays, Re-assign resources | Project Manager | 2010-03-01 | 2011-03-31 | 2010-03-01 | 2011-03-31 | 300000 | 0 | 1.4.3 | Proposed | L | M | M | M | 10
Fixed-rate financing, Interest rate swaps | R016 | Monitor market trends and consider locking in interest rates through hedging instruments. | Chief Financial Manager | 2008-05-01 | 2008-12-31 | 2008-05-01 | 2008-12-31 | 1600000 | 0 | 1.4.4 | Proposed | L | L | M | L | 7.3
Currency Risk Mitigation Framework | R017 | Measures to manage currency fluctuations were essential to protect the project's financial stability. | Chief Financial Officer | 2008-05-01 | 2008-12-31 | 2008-05-01 | 2008-12-31 | 375000 | 0 | 1.4.5 | Proposed | L | L | L | VL | 6
Cybersecurity Risk Management | R018 | Cybersecurity vulnerabilities could lead to data loss, system downtime, reputation damage, and financial losses through regulatory fines or legal fees. | IT Security Team | 2008-06-01 | 2018-10-06 | 2008-06-01 | 2018-10-06 | 550000 | 0 | 1.4.6 | Proposed | M | M | H | M | 28
Enhanced Stakeholder Engagement | R019 | Implement a comprehensive communications plan to address stakeholder concerns and improve transparency. | Project Manager | 2010-03-01 | 2011-03-31 | 2010-03-01 | 2011-03-31 | 385000 | 0 | 1.4.3 | InProgress | VL | L | M | M | 4
Differentiation through Environmental and Efficiency Standards | R020 | Setting higher environmental and efficiency standards aims to surpass regulatory norms, optimize operations, and establish the organization as a leader in sustainability and efficiency within its industry. | CTO or COO | 2011-04-06 | 2011-05-12 | 2011-04-06 | 2011-05-12 | 270000 | 0 | 1.5.1 | Proposed | M | M | H | H | 35
Supplier diversification and multiple sourcing | R021 | Supplier diversification and multiple sourcing mitigate supply chain risks through redundancy and flexibility | Supply Chain Manager | 2011-05-11 | 2011-10-20 | 2011-05-11 | 2011-10-20 | 500000 | 0 | 1.5.2 | Proposed | M | M | L | M | 25

## Task Impacts
|  |  | Schedule |  |  |  | Cost
Scenario Name | Risk ID | WBS/Task ID | Shape | Minimum | Likely | Maximum | Cost Shape | Cost Minimum | Cost Likely | Cost Maximum
Pre-mitigation | R001 | 1.1.1 | Triangle | 2 | 5 | 7 | Triangle | 416000 | 520000 | 650000
Pre-mitigation | R002 | 1.1.2 | Triangle | 2 | 5 | 7 | Triangle | 352000 | 440000 | 550000
Pre-mitigation | R003 | 1.1.3 | Triangle | 2 | 5 | 7 | Triangle | 150000 | 300000 | 350000
Pre-mitigation | R004 | 1.1.4 | Triangle | 2 | 5 | 7 | Triangle | 150000 | 250000 | 300000
Pre-mitigation | R005 | 1.2.1 | Triangle | 2 | 5 | 7 | Triangle | 100000 | 200000 | 250000
Pre-mitigation | R006 | 1.2.2 | Triangle | 2 | 5 | 7 | Triangle | 24800 | 31000 | 38750
Pre-mitigation | R007 | 1.2.3 | Triangle | 2 | 5 | 7 | Triangle | 26400 | 33000 | 41250
Pre-mitigation | R008 | 1.2.4 | Triangle | 2 | 5 | 9 | Triangle | 850000 | 1000000 | 1100000
Pre-mitigation | R009 | 1.3.1 | Triangle | 2 | 5 | 7 | Triangle | 360000 | 450000 | 562500
Pre-mitigation | R010 | 1.3.2 | Triangle | 2 | 5 | 7 | Triangle | 448000 | 560000 | 700000
Pre-mitigation | R011 | 1.3.3 | Triangle | 2 | 5 | 7 | Triangle | 200000 | 400000 | 450000
Pre-mitigation | R012 | 1.3.4 | Triangle | 2 | 5 | 7 | Triangle | 400000 | 500000 | 625000
Pre-mitigation | R013 | 1.4.1 | Triangle | 2 | 5 | 7 | Triangle | 176000 | 220000 | 275000
Pre-mitigation | R014 | 1.4.2 | Triangle | 2 | 5 | 7 | Triangle | 750000 | 800000 | 920000
Pre-mitigation | R015 | 1.4.3 | Triangle | 2 | 5 | 9 | Triangle | 396000 | 500000 | 600000
Pre-mitigation | R016 | 1.4.4 | Triangle | 2 | 5 | 7 | Triangle | 1450000 | 2000000 | 2200000
Pre-mitigation | R017 | 1.4.5 | Triangle | 2 | 5 | 7 | Triangle | 296000 | 370000 | 462500
Pre-mitigation | R018 | 1.4.6 | Triangle | 2 | 5 | 7 | Triangle | 412500 | 550000 | 687500
Pre-mitigation | R019 | 1.4.3 | Triangle | 2 | 5 | 7 | Triangle | 385000 | 500000 | 585000
Pre-mitigation | R020 | 1.5.1 | Triangle | 2 | 5 | 7 | Triangle | 320000 | 400000 | 500000
Pre-mitigation | R021 | 1.5.2 | Triangle | 2 | 5 | 7 | Triangle | 400000 | 500000 | 600000

## Options (hidden)
<Options><IncludeRisksWithScore>false</IncludeRisksWithScore><HiddenColumns Name="untitled"/><IncludeRisksWithScoreNum>0</IncludeRisksWithScoreNum><DefaultShape>3</DefaultShape><MaxVHValue>2.000000</MaxVHValue><SpreadCosts>true</SpreadCosts><SpreadDurations>true</SpreadDurations><CostsIncludeDur>false</CostsIncludeDur><ShowImpactsAsPercent>false</ShowImpactsAsPercent><LinkImpacts>true</LinkImpacts><AutoPopulateTaskImpacts>true</AutoPopulateTaskImpacts><rgbThreat>5992447</rgbThreat><rgbOpportunity>12561751</rgbOpportunity><rgbCurrent>14871722</rgbCurrent><rgbTarget>9602507</rgbTarget><rgbMitigate>16777215</rgbMitigate><rgbEliminate>16777215</rgbEliminate><rgbAccept>16777215</rgbAccept><rgbTransfer>16777215</rgbTransfer></Options>
<UserFieldDefinitions><UserFieldDefinition ID="{E8C40036-8B26-4DC7-82E1-8350F145F83F}"><ID>{E8C40036-8B26-4DC7-82E1-8350F145F83F}</ID><Name>UserText1</Name><Type>Text</Type></UserFieldDefinition><UserFieldDefinition ID="{0D50B242-233B-4A65-B070-AC0D8FE7399E}"><ID>{0D50B242-233B-4A65-B070-AC0D8FE7399E}</ID><Name>UserText2</Name><Type>Text</Type></UserFieldDefinition><UserFieldDefinition ID="{954B7D84-CEB2-449E-BC85-1D67D9533E9D}"><ID>{954B7D84-CEB2-449E-BC85-1D67D9533E9D}</ID><Name>UserText3</Name><Type>Text</Type></UserFieldDefinition><UserFieldDefinition ID="{461E22CD-2DA4-49FD-9F28-A64470A3E363}"><ID>{461E22CD-2DA4-49FD-9F28-A64470A3E363}</ID><Name>UserText4</Name><Type>Text</Type></UserFieldDefinition><UserFieldDefinition ID="{EACF91EF-9082-4492-BFEA-7C9CF6DA3D4E}"><ID>{EACF91EF-9082-4492-BFEA-7C9CF6DA3D4E}</ID><Name>UserText5</Name><Type>Text</Type></UserFieldDefinition><UserFieldTabName>User Defined</UserFieldTabName></UserFieldDefinitions>
<PID><LevelTypes><LevelType Name="Tolerance"><Levels><Level Position="0"><ShortName>N</ShortName><FullName>Negligible</FullName><Color>#969696</Color></Level><Level Position="1"><ShortName>L</ShortName><FullName>Low</FullName><Color>#00FF00</Color></Level><Level Position="2"><ShortName>M</ShortName><FullName>Medium</FullName><Color>#FFFF00</Color></Level><Level Position="3"><ShortName>H</ShortName><FullName>High</FullName><Color>#FF0000</Color></Level></Levels></LevelType><LevelType Name="Proximity"><Levels><Level Position="0"><ShortName>N</ShortName><FullName>Overdue</FullName><Color>#FF0000</Color></Level><Level Position="1"><ShortName>I</ShortName><FullName>Imminent</FullName><Color>#FF0000</Color></Level><Level Position="2"><ShortName>M</ShortName><FullName>Mid Term</FullName><Color>#FFFF00</Color></Level><Level Position="3"><ShortName>D</ShortName><FullName>Distant</FullName><Color>#00FF00</Color></Level></Levels></LevelType><LevelType Name="Manageability"><Levels><Level Position="0"><ShortName>N</ShortName><FullName></FullName><Color>#FFFFFF</Color></Level><Level Position="1"><ShortName>E</ShortName><FullName>Easy</FullName><Color>#00FF00</Color></Level><Level Position="2"><ShortName>M</ShortName><FullName>Moderate</FullName><Color>#FFFF00</Color></Level><Level Position="3"><ShortName>D</ShortName><FullName>Difficult</FullName><Color>#FF0000</Color></Level></Levels></LevelType><LevelType Name="Impacts"><Levels><Level Position="0"><ShortName>N</ShortName><FullName>Negligible</FullName><Color>#FFFFFF</Color></Level><Level Position="1"><ShortName>VL</ShortName><FullName>Very Low</FullName><Color>#FFFFFF</Color></Level><Level Position="2"><ShortName>L</ShortName><FullName>Low</FullName><Color>#FFFFFF</Color></Level><Level Position="3"><ShortName>M</ShortName><FullName>Medium</FullName><Color>#FFFFFF</Color></Level><Level Position="4"><ShortName>H</ShortName><FullName>High</FullName><Color>#FFFFFF</Color></Level><Level Position="5"><ShortName>VH</ShortName><FullName>Very High</FullName><Color>#FFFFFF</Color></Level></Levels></LevelType><LevelType Name="Probability"><Levels><Level Position="0"><ShortName>N</ShortName><FullName>Negligible</FullName><Color>#FFFFFF</Color></Level><Level Position="1"><ShortName>VL</ShortName><FullName>Very Low</FullName><Color>#FFFFFF</Color></Level><Level Position="2"><ShortName>L</ShortName><FullName>Low</FullName><Color>#FFFFFF</Color></Level><Level Position="3"><ShortName>M</ShortName><FullName>Medium</FullName><Color>#FFFFFF</Color></Level><Level Position="4"><ShortName>H</ShortName><FullName>High</FullName><Color>#FFFFFF</Color></Level><Level Position="5"><ShortName>VH</ShortName><FullName>Very High</FullName><Color>#FFFFFF</Color></Level></Levels></LevelType></LevelTypes><Tolerance Name="Tolerance"><Thresholds LevelName="Tolerance"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>Up to 5</Description><FullLevelDescription>L (Up to 5)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>5</Value><Description>5 to 23</Description><FullLevelDescription>M (5 to 23)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>23</Value><Description>23 or higher</Description><FullLevelDescription>H (23 or higher)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Tolerance</Name><Order>0</Order><UseImpact>true</UseImpact><Type>Tolerance</Type><LevelType>Tolerance</LevelType></Tolerance><Proximity Name="Proximity"><Thresholds LevelName="Proximity"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>0</Description><FullLevelDescription>I (0)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>60</Value><Description>60</Description><FullLevelDescription>M (60)</FullLevelDescription><Weighting>0.900000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>180</Value><Description>180</Description><FullLevelDescription>D (180)</FullLevelDescription><Weighting>0.800000</Weighting></Threshold></Thresholds><Name>Proximity</Name><Order>0</Order><UseImpact>false</UseImpact><Type>Proximity</Type><LevelType>Proximity</LevelType></Proximity><Manageability Name="Manageability"><Thresholds LevelName="Manageability"><Threshold Level="1"><Level>1</Level><Value>Requires minimal changes to project baseline</Value><Description>Requires minimal changes to project baseline</Description><FullLevelDescription>E (Requires minimal changes to project baseline)</FullLevelDescription><Weighting>1.100000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>Requires some changes to project baseline</Value><Description>Requires some changes to project baseline</Description><FullLevelDescription>M (Requires some changes to project baseline)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>Requires many changes to project baseline</Value><Description>Requires many changes to project baseline</Description><FullLevelDescription>D (Requires many changes to project baseline)</FullLevelDescription><Weighting>0.900000</Weighting></Threshold></Thresholds><Name>Manageability</Name><Order>0</Order><UseImpact>false</UseImpact><Type>User</Type><LevelType>Manageability</LevelType></Manageability><ImpactDefinitions><ImpactDefinition Name="Schedule"><Thresholds LevelName="Impacts"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>Up to 5</Description><FullLevelDescription>VL (Up to 5)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>5</Value><Description>5 to 10</Description><FullLevelDescription>L (5 to 10)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>10</Value><Description>10 to 20</Description><FullLevelDescription>M (10 to 20)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="4"><Level>4</Level><Value>20</Value><Description>20 to 40</Description><FullLevelDescription>H (20 to 40)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="5"><Level>5</Level><Value>40</Value><Description>40 or higher</Description><FullLevelDescription>VH (40 or higher)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Schedule</Name><Order>0</Order><UseImpact>true</UseImpact><Type>Schedule</Type><LevelType>Impacts</LevelType></ImpactDefinition><ImpactDefinition Name="Cost"><Thresholds LevelName="Impacts"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>Up to $5,000</Description><FullLevelDescription>VL (Up to $5,000)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>5,000</Value><Description>$5,000 to $10,000</Description><FullLevelDescription>L ($5,000 to $10,000)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>10,000</Value><Description>$10,000 to $25,000</Description><FullLevelDescription>M ($10,000 to $25,000)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="4"><Level>4</Level><Value>25,000</Value><Description>$25,000 to $50,000</Description><FullLevelDescription>H ($25,000 to $50,000)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="5"><Level>5</Level><Value>50,000</Value><Description>$50,000 or higher</Description><FullLevelDescription>VH ($50,000 or higher)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Cost</Name><Order>1</Order><UseImpact>true</UseImpact><Type>Cost</Type><LevelType>Impacts</LevelType></ImpactDefinition><ImpactDefinition Name="Performance"><Thresholds LevelName="Impacts"><Threshold Level="1"><Level>1</Level><Value>Failure to meet a minor acceptance criteria</Value><Description>Failure to meet a minor acceptance criteria</Description><FullLevelDescription>VL (Failure to meet a minor acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>Failure to meet more than one minor acceptance criteria</Value><Description>Failure to meet more than one minor acceptance criteria</Description><FullLevelDescription>L (Failure to meet more than one minor acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>Shortfall in meeting acceptance criteria</Value><Description>Shortfall in meeting acceptance criteria</Description><FullLevelDescription>M (Shortfall in meeting acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="4"><Level>4</Level><Value>Significant shortfall in meeting acceptance criteria</Value><Description>Significant shortfall in meeting acceptance criteria</Description><FullLevelDescription>H (Significant shortfall in meeting acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="5"><Level>5</Level><Value>Failure to meet acceptance criteria</Value><Description>Failure to meet acceptance criteria</Description><FullLevelDescription>VH (Failure to meet acceptance criteria)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Performance</Name><Order>2</Order><UseImpact>true</UseImpact><Type>User</Type><LevelType>Impacts</LevelType></ImpactDefinition></ImpactDefinitions><Probability Name="Probability"><Thresholds LevelName="Probability"><Threshold Level="1"><Level>1</Level><Value>0</Value><Description>Up to 10%</Description><FullLevelDescription>VL (Up to 10%)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="2"><Level>2</Level><Value>10</Value><Description>10% to 30%</Description><FullLevelDescription>L (10% to 30%)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="3"><Level>3</Level><Value>30</Value><Description>30% to 50%</Description><FullLevelDescription>M (30% to 50%)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="4"><Level>4</Level><Value>50</Value><Description>50% to 70%</Description><FullLevelDescription>H (50% to 70%)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold><Threshold Level="5"><Level>5</Level><Value>70</Value><Description>70% or higher</Description><FullLevelDescription>VH (70% or higher)</FullLevelDescription><Weighting>1.000000</Weighting></Threshold></Thresholds><Name>Probability</Name><Order>0</Order><UseImpact>true</UseImpact><Type>Probability</Type><LevelType>Probability</LevelType></Probability><Scores><Score Probability="1" Impact="1" Color="#00FF00">1</Score><Score Probability="1" Impact="2" Color="#00FF00">1</Score><Score Probability="1" Impact="3" Color="#00FF00">2</Score><Score Probability="1" Impact="4" Color="#00FF00">4</Score><Score Probability="1" Impact="5" Color="#FFFF00">8</Score><Score Probability="2" Impact="1" Color="#00FF00">2</Score><Score Probability="2" Impact="2" Color="#00FF00">3</Score><Score Probability="2" Impact="3" Color="#FFFF00">6</Score><Score Probability="2" Impact="4" Color="#FFFF00">12</Score><Score Probability="2" Impact="5" Color="#FF0000">24</Score><Score Probability="3" Impact="1" Color="#00FF00">3</Score><Score Probability="3" Impact="2" Color="#00FF00">5</Score><Score Probability="3" Impact="3" Color="#FFFF00">10</Score><Score Probability="3" Impact="4" Color="#FFFF00">20</Score><Score Probability="3" Impact="5" Color="#FF0000">40</Score><Score Probability="4" Impact="1" Color="#00FF00">4</Score><Score Probability="4" Impact="2" Color="#FFFF00">7</Score><Score Probability="4" Impact="3" Color="#FFFF00">14</Score><Score Probability="4" Impact="4" Color="#FF0000">28</Score><Score Probability="4" Impact="5" Color="#FF0000">56</Score><Score Probability="5" Impact="1" Color="#00FF00">5</Score><Score Probability="5" Impact="2" Color="#FFFF00">9</Score><Score Probability="5" Impact="3" Color="#FFFF00">18</Score><Score Probability="5" Impact="4" Color="#FF0000">36</Score><Score Probability="5" Impact="5" Color="#FF0000">72</Score></Scores><Source>7.82</Source><ScoreMethod>Highest</ScoreMethod></PID>
<SourceProjectID>-1</SourceProjectID>
<PlanData><TotalTaskCount>26</TotalTaskCount><InProgressTaskCount>0</InProgressTaskCount><CompletedTaskCount>0</CompletedTaskCount><TimeNow INTVAL="20191203">2019-12-03</TimeNow><DeterministicFinish INTVAL="20210824">2021-08-24</DeterministicFinish><TotalCost>208700.000000</TotalCost><ActualCostToDate>0.000000</ActualCostToDate><RemainingCost>208700.000000</RemainingCost><PrefCurrencySymbol>$</PrefCurrencySymbol><DecimalPlaces>0</DecimalPlaces><DecimalSeparator>.</DecimalSeparator><ThousandSeparator>,</ThousandSeparator><FileName>C:\Users\Jacqu-ee\OneDrive\NEU - Work\PJM Assignments\PJM6015 Assignments\PJM6015_Project Risk Management_2020-2021\Risk Register Sample Plan.plan</FileName><Title>Risk Register Sample Plan.plan</Title></PlanData>
2.1
[AdditionalInfo]
RiskCurProbCol | 4
RiskCurScoreCol | 8
RiskTarProbCol | 12
RiskTarScoreCol | 16
MitActPostProbCol | 13
MitActPostScoreCol | 17
RiskUserFieldOneCol | 30
RiskUserFieldTwoCol | 34